## Sheet1
Project title: | Student Intern Success Analysis |  | Project Id: |  | Project Manager: | Harshada Topale
DOCUMENT VERSION: | 1 |  | Last Updated date: | 2025-04-26 | Project Team Lead: | NA
Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed
RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
Risk | Student Data Includes Personal Information | Data Breach and Mishandling of Data Could Result in Ethical and Legal Issues | Comply With Privacy Regulations | Shaikh Inamul Hasan | Critical |  | Open
Risk | Data Quality Issues | Inaccurate Analysis | Implement data validation and cleaning processes | Shaikh Inamul Hasan | High |  | Open
Risk | Stakeholder availability | Communication Issue May Arise | Schedule regular meetings and ensure clear communication | Shaikh Inamul Hasan | High |  | Open
Assumption | Data provided is accurate | Project results may be inaccurate | Conduct data quality checks and validation before analysis | Shaikh Inamul Hasan | Moderate |  | Open
Assumption | Access to other tools | Delays in analysis and visualization | These tools are commonly used in the department and are expected to be readily available. | Shaikh Inamul Hasan | Moderate |  | Open
Issue | Missing data in some records | Missing data can lead to incomplete analysis | Implement data cleaning processes to fill missing values appropriately | Shaikh Inamul Hasan | High |  | Open
Issue | Technical difficulties with Power BI | Technical issues with Power BI can hinder the creation of visualizations, resulting in delays and potential gaps in the data presentation. | Seek technical support from any Learning Platform | Shaikh Inamul Hasan | High |  | Open
Dependency | Data access from various colleges | Without timely access to data from various colleges, the project cannot proceed with the planned analysis, leading to significant delays | Establish data sharing agreements early in the project and maintain regular communication with data providers to ensure timely access. | Shaikh Inamul Hasan | Moderate |  | Open
Dependency | The project relies on data visualization tools to present results | Inability to access these tools would hinder the presentation of insights | Ensure access to preferred data visualization tools | Shaikh Inamul Hasan | Critical |  | Open