## Sheet1
PROJECT NAME | Data Analysis
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE | Specialized portal for data analysts.
PROJECT START DATE | 2025-04-26
PROJECT END DATE | 2025-06-26
OVERALL PROGRESS | Done
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | Initiation |  |  |  | 3
| 1.1 Identify business problem |  |  |  | 3 | COMPLETED
| 1.2 Recruit a team (Solo) |  |  |  | 1 | COMPLETED
| 1.3 Create a project charter |  |  |  | 2 | COMPLETED
| 1.4 Requirement gathering |  |  |  | 2 | COMPLETED
2 | Planning |  |  |  | 6
| 2.1 Approval of business process |  |  |  | 2
| 2.2 Baseline project plan |  |  |  | 2
| 2.3 Team roles and responsibilities (Solo) |  |  |  | 2 | COMPLETED
3 | Execution |  |  |  | 49 | COMPLETED
| 3.1 Finalize design |  |  |  | 5 | COMPLETED
| 3.2 Build |  |  |  | 34
| 3.2.1 Features |  |  |  | 13
| • Registration/Login for candidates & employers |  |  |  | 3
| • Home Page with navigation bar |  |  |  | 4 | COMPLETED
| • Job listing/search with filters |  |  |  | 5 | IN PROGRESS
| • Job detail page + Apply button |  |  |  | 4
| • Employer dashboard & post job feature |  |  |  | 5
| • Profile section for users |  |  |  | 4
| • Footer, links & static info |  |  |  | 2
| 3.3 Testing |  |  |  | 7
| • Manual + Automation Testing |  |  |  | 7
4 | Closure |  |  |  | 1